## Sheet1
Number | Title | Sequence | Related Issues | Date Opened | Status | Date Closed | Comments | Response / Test
89 | IPixelMapTransformSource | -1 |  | 2019-07-16 | OPEN |  | remove PixelChain dependency on IpixelMapTransformSource
90 | NONE CODE | -1 |  | 2019-07-16 | CLOSED |  | How to make lines moother … do I need positions in Vertex | Ivertex now has an position
79 | Auto Update Curves | 0 |  | 2019-07-12 | CLOSED |  | If you click AUC then the Updated curves button goes away … and the view might be out of date … and you cant refresh it without making a change. Should track isDirty and do an update if needed. | renemed stuff to Auto
80 | Show graffiti | 0 |  | 2019-07-12 | CLOSED |  | There is an option to show Graftiti … but it only controls the segment grafiti. Should be able to hide/make transparent the pixels too. | Can change the opacity of the grafitti colors
81 | Mis matched lines | 0 | 90 | 2019-07-12 | OPEN |  | it would be good to have an option to show where segments are not smoothly matched. Possibly by coloring the pixel different
82 | draw cursor | 0 |  | 2019-07-12 | OPEN |  | is there any need for mMouseLastPixelPosition now that graffitiCuror is bing used.
83 | Make lines smooth | 0 | 89 | 2019-07-12 | OPEN
84 | Join broken lines | 0 |  | 2019-07-12 | OPEN
85 | Change EPMD into state based app | 0 |  | 2019-07-12 | OPEN
86 | ControlBase | 0 |  | 2019-07-14 | CLOSED |  | add Typed Listeners, Validators and make fluent.
87 | Fix errors that prevent mvn clean build | 0 |  | 2019-07-16 | OPEN
64 | Contained project | 1 |  | 2017-01-03 | DONE |  | Need to have a test image available in the project set so that it can be opened on different platforms
29 | Proper startup | 1 |  | 2016-09-07 | CLOSED |  | Need to run this from the javafx application class
63 | FileSave | 1 |  | 2017-01-02 | OPEN |  | Needs to repsect the size of the image (currently opens NY2)
40 | Create Dialog | 1 | 30 | 2016-09-08 | CLOSED | 2016-09-08 | now have a create dialog option in ViewFactory
60 | Sorted Transform names | 1 |  | 2017-01-01 | CLOSED |  | When you add a transform to the transform stack the list of transforms is not sorted.
27 | AppControlView singleton | 1 |  | 2016-08-23 | CLOSED | 2016-09-07 | Why does com.ownimage.perception.view.javafx.AppControlView need to be a singleton | KH 23/8 at the moment I am not convinced that it does KH 7/9 there is a relationship with the app to how it is able to create dialogs. Perhaps it does not need to be a singleton … but there should be a single reference from the IAppControl
52 | Can not enter freeform name into logger | 1 | 30 | 2016-09-11 | CLOSED | 2016-09-11
53 | logging load | 1 | 30 | 2016-09-11 | CLOSED | 2016-09-16
54 | logging save, save as | 1 | 30 | 2016-09-11 | CLOSED | 2016-09-16
55 | need fileControl save dialog | 1 | 54 | 2016-09-16 | CLOSED | 2016-09-16
61 | Need to finishe File, FileOpen etc | 1 |  | 2017-01-01 | OPEN
66 | When inserting or deleting transform shoud update image | 1 |  | 2017-01-03 | DONE
30 | Logging to menu | 2 | 40,41,52,53,54 | 2016-09-07 | CLOSED |  | Currently there are too many System.outs in the code. Need to start using logging properly. This means adding the logging read/write/edit to the FileSystemMenu based on the -TEST option and replacing the System.outs | Change log levels is a submenu off Properties. I think that it should have a menu of its own
41 | Combo box | 2 | 30 | 2016-09-09 | CLOSED | 2016-09-10 | Need to have an object selection combo box
62 | Double Control BOTH | 2 |  | 2017-01-02 | OPEN |  | The display is not respecting the DoubleMetaType display BOTH … i.e. can not display the slider.
31 | Properties | 3 | 33, 46 | 2016-09-07 | OPEN |  | Need to have the properties dialog (with the FX tab), inc save, edit etc. | private final DoubleControl mDoubleControl = new DoubleControl("DoubleControl", "doubleControl", new Container("Container", "container"), 0.2); public final IProperty<Double> doubleProperty = mDoubleControl;
65 | Can JavaFX use the Mac manus | 3 |  | 2017-01-03 | OPEN
32 | Remove unused code | 4 |  | 2016-09-07 | OPEN |  | specifically the com.ownimage.perception.control.grafitti should keep the path and what is possible from the GraphicsHelper
33 | Properties of Properties | 5 | 30 | 2016-09-07 | OPEN |  | Should I expose some of the properties as Iproperty<> to save having to create getters and setters for them. Specifically thinking of the Properties class here.
34 | JOCL | 8 |  | 2016-09-07 | OPEN
35 | Status bar | 9 |  | 2016-09-07 | OPEN |  | Need to have CPU usage, number of jobs in Queue etc on the status bar.
38 | Load/Save default transform | 9 |  | 2016-09-07 | OPEN |  | Needs to have transform load save working
36 | Recently added files list | 9 |  | 2016-09-07 | OPEN
37 | Help version # | 9 |  | 2016-09-07 | OPEN
57 | FileControl | 9 |  | 2016-09-16 | OPEN |  | Need better way to handle file the base direcotry that the file chooser opens at (or default value for file)
71 | remove Framework.checkParameterNotNull | 9 |  | 2019-07-11 | OPEN |  | Need to check what runtime issues this might cause as I did have a problem in EPMD
77 | mResultantPixelMap | 9 |  | 2019-07-12 | OPEN |  | This looks like a source of errors
73 | PixelMap transformGetLineColor uses default divisor of 1000 | 9 |  | 2019-07-11 | OPEN
50 | Better constructor for ObjectControl | 10 |  | 2016-09-11 | OPEN |  | ObjectStringMetaType loggerNameMetaModel = new ObjectStringMetaType(loggerNames, true, true); ObjectType<String> loggerNameType = new ObjectType<>("", loggerNameMetaModel); ObjectControl<String> loggerNameControl = new ObjectControl<>("Loggers", "loggers", edit, loggerNameType);
51 | Better ctor for ActionControl with some form of null container | 10 |  | 2016-09-11 | CLOSED | 2016-09-11 | ActionControl(DisplayName, action); … there are static create methods in ActionControl
46 | Performance.getProperties | 10 | 31 | 2016-09-09 | OPEN |  | move to app base
45 | undoRedobuffer references | 10 |  | 2016-09-09 | OPEN |  | remove the dependency on Perception.getUndo as not all applications will be Perception. Can move this to UndoRedo or to some system level class directly, e.g. appbase.
48 | BaseType and metatype | 10 |  | 2016-09-09 | OPEN |  | setValue returns true or false rather than throwing an exception … investigate
49 | Split out Framework | 10 |  | 2016-09-11 | DONE |  | Split out all of the perception Framework into com.ownimage.framework
47 | ControlBase mValid | 10 |  | 2016-09-09 | OPEN |  | What is this used for … can it be removed
44 | Platform Runlater | 10 |  | 2016-09-09 | OPEN
58 | NamedTabs | 99 |  | 2016-10-15 | OPEN |  | if you display a NamedTabs with no contnt then it throws an exception
56 | FileControl | 99 | 55 | 2016-09-16 | OPEN |  | Need better factory methods for FileControl
59 | Loggin | 99 |  | 2016-10-15 | OPEN |  | Not all logs are being captured in the log editor .. Possibly ones created with FrameworkLogger
21 | View Required | 99 |  |  | OPEN |  | VerticalDivider
20 | View Required | 99 |  |  | OPEN |  | VerticalFlow
43 | Application icon | 99 |  | 2016-09-09 | OPEN |  | Want a new application icon
18 | double add | 99 |  |  | CLOSED | 2016-09-11 | What should happen if you add a control to a container twice. | It is aded to the container twice
42 | Startup splash screen | 99 |  | 2016-09-09 | OPEN
88 | @NotNull | 99 |  | 2019-07-16 | OPEN |  | @NotNull different code is generated in IntelliJ to Maven hence leads to different test results
5 | addView |  |  |  | CLOSED |  | Can I move the control addView to ControlBase IView view = ViewFactory.getInstance().createView((C) this); does not work with the generic
26 | EventDispatcher |  |  |  | CLOSED |  | create a generic event dispatcher
11 | control clone() |  |  |  | CLOSED |  | following from issue 3 should there be a clone() with no parameters
25 | View Required |  |  |  | CLOSED |  | Grafitti Picture
24 | View Required |  |  |  | CLOSED |  | HorizontalDivider
23 | View Required |  |  |  | CLOSED |  | HorizontalFlow
3 | addChild |  |  |  | CLOSED |  | in container should be addContainer
7 | nested class Action |  |  |  | CLOSED |  | Move ActionControl.Action to Iaction
22 | View Required |  |  |  | CLOSED |  | NamedTabs
39 | AppControlView singleton |  | 27 | 2016-09-07 | CLOSED | 2016-09-08 | Need a way to recover the AppControlView singleton so that size changes etc can be passed to it. | Cannot return the value as we do with other controls as creating the app might not return the value. Sholuld have a getAppView in viewFactory.
74 | EPMD off on an off pixel caused redraw |  |  | 2019-07-11 | CLOSED |  | proved not to be an issue
16 | tidy |  |  |  | CLOSED |  | put setVisible and setEnabled into Viewbase
67 | check why graffiti is not drawn properly when action on drag is performed on long chains ( |  |  |  | CLOSED |  | segments are not drawn properly
4 | control constructor |  |  |  | CLOSED |  | Should controls be able to be created without a container
2 | clone |  |  |  | CLOSED |  | Should controls support clone(container)
6 | BoolenControl has getBoolean |  |  |  | CLOSED |  | should it use the more generic getValue
8 | control setTransient |  |  |  | CLOSED |  | should return C
9 | control setEnabled |  |  |  | CLOSED |  | should return C
10 | control setVisible |  |  |  | CLOSED |  | should return C
12 | containr getXControl |  |  |  | CLOSED |  | these should be removed
69 | in EPMD the status of all the controls is not properly shown in all cases. |  |  | 2019-07-11 | CLOSED |  | This is an initialization issue
75 | Since Issue 70 redraw is slower … optimize |  |  | 2019-07-11 | CLOSED |  | This seems to have gone away
19 | View Required |  |  |  | CLOSED |  | VerticalTab | This was replaced with the AccordionView
68 | Add visual marker |  |  | 2019-07-11 | CLOSED |  | when performing an action in EPMD it might take a while for it to be shown … e.g. change thickness … should have a visual marker
28 | IAppControl argument |  |  | 2016-08-23 | CLOSED | 2016-08-23 | Why does com.ownimage.perception.view.javafxAppControlView take IAppControl as an argument in theViewFactory when all the other components take the raw types, e.g. BooleanControl | KH 23/8 This is because there could be many different apps, e.g. Perception, ImageOrganizer and the ViewFactory needs a common ancestor for all of them.
13 | need ColorControl |  |  |  | CLOSED
14 | boolean control not lining up on screen |  |  |  | CLOSED
15 | color control squiching |  |  |  | CLOSED
17 | ContainerView |  |  |  | CLOSED
70 | large thickness cause clipping |  |  | 2019-07-11 | CLOSED
72 | EPMD make it reopen in the same state that it closed in |  |  | 2019-07-11 | CLOSED
76 | Graffiti lines are offset from pixels |  |  | 2019-07-11 | CLOSED
78 | CannyTransform generate egdes needs to disable EditPixels |  |  | 2019-07-12 | CLOSED